## Sheet1
Planned Gantt Chart
[5 empty] | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | Week Beginning
Task Title | Task Description | Proposed Duration | Start Week | End Week | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Week Number
PRETEND TASK | WRITING X PART OF THE REPORT | Develop Artifact | 49 | 3 | bar: 2024-12-02 to 2025-01-20
Pretend Sub Task 1 | Some starting part for it | Implement any supervisor feedback | 1 | 1 | bar: 2025-01-27
Pretend Sub Task 2 | Some later part for it | Downtime to complete other 3rd year modules | 2 | 2 | bar: 2025-02-03 to 2025-03-10
User Testing | bar: 2025-02-03 to 2025-02-10
Design/Implementation Report Writing | bar: 2025-03-17
User Testing Processing and Report Writing | bar: 2025-03-24
Incremental Litreture Review | bar: 2025-03-24 to 2025-03-31
Project Management Report Writing | bar: 2025-03-31
Abstract | bar: 2025-04-07
Conclusion | bar: 2025-04-07
Polish | bar: 2025-04-07 to 2025-04-14
Actual Gantt Chart
[5 empty] | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | Week Beginning
Task Title | Task Description | Actual Duration | Start Week | End Week | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Week Number
PRETEND TASK | WRITING X PART OF THE REPORT | Develop Artifact | 49 | 3 | bar: 2024-12-02 to 2025-01-27
Pretend Sub Task 1 | Some starting part for it | Implement any supervisor feedback | 1 | 1 | bar: 2025-01-27
Pretend Sub Task 2 | Some later part for it | Downtime to complete other 3rd year modules | 2 | 2 | bar: 2025-02-03 to 2025-03-10
Pretend New Sub Task | I actually needed to do Y as well | User Testing | bar: 2025-03-17 to 2025-03-24
Design/Implementation Report Writing | bar: 2025-03-17
User Testing Processing and Report Writing | bar: 2025-03-31
Incremental Litreture Review | bar: 2025-03-24 to 2025-03-31
Project Management Report Writing | bar: 2025-04-07
Abstract | bar: 2025-04-07
Conclusion | bar: 2025-04-07
Polish | bar: 2025-04-14